## Sheet1
|  |  |  | Weeks |  | R1 | [6 empty] | R2 |  |  | R3 |  |  |  | R4 |  |  |  | Defensa
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
|  | Start | End | 2020-03-05 | 2020-03-12 | 2020-03-19 | 2020-03-26 | 2020-04-02 | 2020-04-09 | 2020-04-16 | 2020-04-23 | 2020-04-30 | 2020-05-07 | 2020-05-14 | 2020-05-21 | 2020-05-28 | 2020-06-04 | 2020-06-11 | 2020-06-18 | 2020-06-25 | 2020-07-02 | 2020-07-09 | 2020-07-16 | 2020-07-23
Documentation |  | 1 | 16
| Prepare Workspace | 1 | 1 | bar: Weeks 1
| Sections Draft | 1 | 1 | bar: Weeks 1
| Introduction | 1 | 2 | bar: Weeks 1 to Weeks 2
| Project Management | 1 | 2 | bar: Weeks 1 to Weeks 2
| Methodology | 1 | 2 | bar: Weeks 1 to Weeks 2
| State of the Art | 2 | 3 | bar: Weeks 2 to R1 3
| Review Documentation | 3 | 4 | bar: R1 3 to R1 4
| Development | 4 | 17 | bar: R1 4 to R4 17
| Conclusions | 15 | 17 | bar: R3 15 to R4 17
|  | 15 | 17 | bar: R3 15 to R4 17
| Future of the Project | 15 | 17 | bar: R3 15 to R4 17
Data Collection
| UML and Structure | 4 | 4 | bar: R1 4
| Basic Component | 4 | 4 | bar: R1 4
| Component UI | 4 | 5 | bar: R1 4 to R1 5
| Component Funcionality | 5 | 6 | bar: R1 5 to R1 6
| Data Saving | 6 | 6 | bar: R1 6
| Testing | 6 | 6 | bar: R1 6
Data visualization
| UML and Structure | 6 | 7 | bar: R1 7
| Unity Class | 7 | 7 | bar: R1 7 to R1 8
| Visualization GUI | 7 | 8 | bar: R1 7 to R1 8
| Visualization Rendering | 8 | 8 | bar: R1 8
| Data Visualization | 8 | 9 | bar: R1 8 to R1 9
| Testing | 9 | 9 | bar: R1 9
Database
| Database Research | 3 | 3 | bar: R1 3 to R2 10
| Database UML | 10 | 10
| Write to Database | 10 | 11 | bar: R2 10 to R2 11
| Get Data from Database | 11 | 12 | bar: R2 11 to R2 12
| Local Database | 12 | 13 | bar: R2 12 to R3 13
| Remote Database | 13 | 14 | bar: R3 13 to R3 14
QA
| Project Simulation | 14 | 14 | bar: R3 14
Publishing to Unity | bar: Weeks 1 to R4 17
| Look into Asset Store Publishing | 15 | 15 | bar: R3 15
| Prepare Assets | 15 | 15 | bar: R3 15
| Publish | 15 | 15 | bar: R3 15